AQAR.AI

AI-Driven Cross-Platform Real Estate Aggregator

User Stories, Sprint Backlog & Issue Tracker

Master Thesis — SDLC Documentation

Generated: 2026-05-11

# Table of Contents

# Project Summary

| Metric | Value |
| --- | --- |
| Total Sprints | 10 (20 weeks) |
| Total User Stories | 37 |
| Total GitHub Issues | 112 |
| Total Story Points | 173 |
| Average Points/Sprint | 17.3 |

## Sprint Roadmap Overview

| Sprint | Name | Weeks | Stories | Points | Focus |
| --- | --- | --- | --- | --- | --- |
| S1 | Foundation & Scaffold | 1-2 | 5 | 23 | Infrastructure |
| S2 | Video Ingestion Pipeline | 3-4 | 4 | 16 | Pipeline |
| S3 | Transcription Pipeline | 5-6 | 3 | 16 | AI/ML |
| S4 | LLM Data Extraction | 7-8 | 4 | 19 | AI/ML |
| S5 | Geocoding & Storage | 9-10 | 4 | 18 | Pipeline |
| S6 | API & Search | 11-12 | 4 | 15 | Backend |
| S7 | Web Portal | 13-14 | 4 | 21 | Frontend |
| S8 | Mobile App | 15-16 | 3 | 16 | Mobile |
| S9 | Quality & Monitoring | 17-18 | 3 | 13 | DevOps |
| S10 | Deployment & Thesis | 19-20 | 3 | 16 | DevOps |

# Sprint 1: Foundation & Scaffold

Weeks: 1-2

Sprint Goal: Monorepo structure, Docker dev stack, CI/CD, database schema, and baseline API running end-to-end.

Capacity: 5 stories, 23 points, 16 issues

| ID | User Story | Priority | Points | Type | Title |
| --- | --- | --- | --- | --- | --- |
| US-001 | As a developer, I want a well-organized monorepo with clear package boundaries so that I can navi... | P0 | 5 | Infrastructure | Project Scaffold & Monorepo |
| US-002 | As a developer, I want a single command to spin up all services locally so that I can develop wit... | P0 | 5 | Infrastructure | Docker Development Stack |
| US-003 | As a developer, I want a well-defined database schema so that all pipeline stages can store and r... | P0 | 8 | Backend | Database Schema & Migrations |
| US-004 | As a developer, I want automated linting, testing, and Docker build validation on every PR so tha... | P0 | 3 | DevOps | CI/CD Pipeline |
| US-005 | As an operator, I want health check endpoints so that I can monitor service availability and depe... | P1 | 2 | Backend | Health Check API |

## US-001: Project Scaffold & Monorepo

User Story: As a developer, I want a well-organized monorepo with clear package boundaries so that I can navigate and contribute efficiently.

Priority: P0 | Points: 5 | Type: Infrastructure

Acceptance Criteria:

☐  Monorepo with apps/, packages/, infra/ structure exists

☐  All pyproject.toml files define correct dependencies

☐  make dev starts the full Docker Compose stack

☐  make health returns all-green from fresh clone

GitHub Issues:

| Issue ID | Title |
| --- | --- |
| AQAR-001 | Create monorepo directory structure |
| AQAR-002 | Configure root pyproject.toml with ruff/mypy/pytest |
| AQAR-003 | Write Makefile developer commands |

## US-002: Docker Development Stack

User Story: As a developer, I want a single command to spin up all services locally so that I can develop without manual setup.

Priority: P0 | Points: 5 | Type: Infrastructure

Acceptance Criteria:

☐  docker compose up -d starts PostGIS, Redis, Meilisearch, API, Worker, Flower

☐  Health checks ensure proper startup ordering

☐  Volumes persist data across restarts

☐  Hot-reload works for API code changes

GitHub Issues:

| Issue ID | Title |
| --- | --- |
| AQAR-004 | Write Dockerfile.api (multi-stage) |
| AQAR-005 | Write Dockerfile.worker (with FFmpeg) |
| AQAR-006 | Configure docker-compose.yml with all services |
| AQAR-007 | Create init-db.sql with PostGIS extensions |

## US-003: Database Schema & Migrations

User Story: As a developer, I want a well-defined database schema so that all pipeline stages can store and retrieve structured property data.

Priority: P0 | Points: 8 | Type: Backend

Acceptance Criteria:

☐  SQLAlchemy models for VideoSource, Transcript, Property, Location, ProcessingJob

☐  PostGIS geometry column on Location for spatial queries

☐  Alembic migration generates tables from models

☐  All enums (Platform, PropertyType, ListingType, LegalStatus, ProcessingStatus) defined

☐  Indexes on frequently queried columns (price, area, neighborhood, status)

GitHub Issues:

| Issue ID | Title |
| --- | --- |
| AQAR-008 | Define SQLAlchemy models in packages/db |
| AQAR-009 | Configure Alembic for async migrations |
| AQAR-010 | Generate and run initial migration |
| AQAR-011 | Add PostGIS spatial indexes |

## US-004: CI/CD Pipeline

User Story: As a developer, I want automated linting, testing, and Docker build validation on every PR so that code quality is enforced.

Priority: P0 | Points: 3 | Type: DevOps

Acceptance Criteria:

☐  GitHub Actions runs ruff lint on Python code

☐  Unit tests run with PostgreSQL + Redis service containers

☐  Docker images build successfully in CI

☐  Pre-commit hooks configured for local development

GitHub Issues:

| Issue ID | Title |
| --- | --- |
| AQAR-012 | Create .github/workflows/ci.yml |
| AQAR-013 | Configure pre-commit hooks |
| AQAR-014 | Write initial unit test stubs |

## US-005: Health Check API

User Story: As an operator, I want health check endpoints so that I can monitor service availability and dependency status.

Priority: P1 | Points: 2 | Type: Backend

Acceptance Criteria:

☐  GET /health returns 200 with version and environment

☐  GET /health/ready checks Postgres, Redis, Meilisearch and reports status

☐  Degraded status returned if any dependency is down

GitHub Issues:

| Issue ID | Title |
| --- | --- |
| AQAR-015 | Implement /health and /health/ready endpoints |
| AQAR-016 | Add health check integration tests |

# Sprint 2: Video Ingestion Pipeline

Weeks: 3-4

Sprint Goal: Discover YouTube videos from target channels, download audio, and track processing jobs.

Capacity: 4 stories, 16 points, 12 issues

| ID | User Story | Priority | Points | Type | Title |
| --- | --- | --- | --- | --- | --- |
| US-006 | As a system, I want to automatically discover new real estate videos from configured YouTube chan... | P0 | 5 | Pipeline | YouTube Channel Discovery |
| US-007 | As a pipeline stage, I want to download video audio in WAV format so that Whisper can transcribe it. | P0 | 5 | Pipeline | Audio Extraction |
| US-008 | As an operator, I want to track the status and timing of each pipeline stage so that I can monito... | P0 | 3 | Backend | Processing Job Tracking |
| US-009 | As a user, I want to submit a YouTube URL via API so that I can manually trigger processing of a ... | P1 | 3 | Backend | Pipeline Submit API |

## US-006: YouTube Channel Discovery

User Story: As a system, I want to automatically discover new real estate videos from configured YouTube channels so that new listings are captured without manual intervention.

Priority: P0 | Points: 5 | Type: Pipeline

Acceptance Criteria:

☐  Celery beat task runs every 6 hours to check configured channels

☐  New videos (not already in DB) are added to VideoSource table

☐  Video metadata (title, duration, published_at, thumbnail) is captured

☐  Videos longer than MAX_VIDEO_DURATION_MINUTES are skipped

GitHub Issues:

| Issue ID | Title |
| --- | --- |
| AQAR-017 | Implement discover_videos Celery task |
| AQAR-018 | Create YouTube channel configuration (YAML) |
| AQAR-019 | Write yt-dlp metadata extraction wrapper |

## US-007: Audio Extraction

User Story: As a pipeline stage, I want to download video audio in WAV format so that Whisper can transcribe it.

Priority: P0 | Points: 5 | Type: Pipeline

Acceptance Criteria:

☐  yt-dlp downloads audio-only stream from YouTube URL

☐  Audio is converted to WAV format (16kHz mono for Whisper)

☐  Downloaded files stored in configurable DOWNLOAD_PATH

☐  Cleanup deletes audio files after successful transcription

☐  ProcessingJob status updated to 'ingesting' during download

GitHub Issues:

| Issue ID | Title |
| --- | --- |
| AQAR-020 | Implement audio extraction with yt-dlp |
| AQAR-021 | Add FFmpeg audio conversion (WAV 16kHz) |
| AQAR-022 | Implement download cleanup after transcription |

## US-008: Processing Job Tracking

User Story: As an operator, I want to track the status and timing of each pipeline stage so that I can monitor throughput and debug failures.

Priority: P0 | Points: 3 | Type: Backend

Acceptance Criteria:

☐  ProcessingJob status transitions: pending -> ingesting -> transcribing -> extracting -> geocoding -> completed

☐  Stage timings recorded in stage_timings JSONB field

☐  Failed jobs capture error_message, error_stage, error_traceback

☐  Retry counter incremented on each retry attempt

GitHub Issues:

| Issue ID | Title |
| --- | --- |
| AQAR-023 | Implement ProcessingJob state machine |
| AQAR-024 | Add stage timing instrumentation |
| AQAR-025 | Implement retry-failed-jobs Celery task |

## US-009: Pipeline Submit API

User Story: As a user, I want to submit a YouTube URL via API so that I can manually trigger processing of a specific video.

Priority: P1 | Points: 3 | Type: Backend

Acceptance Criteria:

☐  POST /api/v1/pipeline/submit accepts a YouTube URL

☐  Validates URL format (youtube.com or youtu.be)

☐  Returns 409 if URL already submitted

☐  Returns job_id for status polling

☐  Dispatches ingestion Celery task asynchronously

GitHub Issues:

| Issue ID | Title |
| --- | --- |
| AQAR-026 | Implement pipeline submit endpoint |
| AQAR-027 | Add YouTube URL validation |
| AQAR-028 | Connect endpoint to Celery task dispatch |

# Sprint 3: Transcription Pipeline

Weeks: 5-6

Sprint Goal: Transcribe Arabic/Darija audio using Whisper with timestamped segments.

Capacity: 3 stories, 16 points, 8 issues

| ID | User Story | Priority | Points | Type | Title |
| --- | --- | --- | --- | --- | --- |
| US-010 | As a pipeline stage, I want to transcribe audio files using OpenAI Whisper so that spoken propert... | P0 | 8 | AI/ML | Whisper Transcription |
| US-011 | As a researcher, I want to establish transcription quality metrics against a golden dataset so th... | P1 | 5 | AI/ML | Transcription Quality Baseline |
| US-012 | As a pipeline utility, I want to normalize Darija transcription text so that downstream LLM extra... | P2 | 3 | AI/ML | Darija/Arabic Text Normalization |

## US-010: Whisper Transcription

User Story: As a pipeline stage, I want to transcribe audio files using OpenAI Whisper so that spoken property details are converted to text.

Priority: P0 | Points: 8 | Type: AI/ML

Acceptance Criteria:

☐  Whisper large-v3 model processes WAV audio files

☐  Language hint set to Arabic (ar) for better accuracy

☐  Full text and timestamped segments stored in Transcript table

☐  Transcription confidence score calculated and stored

☐  Processing time tracked for performance benchmarking

GitHub Issues:

| Issue ID | Title |
| --- | --- |
| AQAR-029 | Implement Whisper transcription Celery task |
| AQAR-030 | Configure Whisper model loading (CPU/CUDA) |
| AQAR-031 | Implement segment extraction and storage |

## US-011: Transcription Quality Baseline

User Story: As a researcher, I want to establish transcription quality metrics against a golden dataset so that I can measure improvement over time.

Priority: P1 | Points: 5 | Type: AI/ML

Acceptance Criteria:

☐  Golden dataset: 10+ manually transcribed video clips in tests/golden_data/

☐  Word Error Rate (WER) calculated against golden transcripts

☐  make test-ml runs quality benchmarks and reports WER

☐  Baseline WER documented for thesis

GitHub Issues:

| Issue ID | Title |
| --- | --- |
| AQAR-032 | Collect and annotate golden dataset (10 clips) |
| AQAR-033 | Implement WER calculation utility |
| AQAR-034 | Create ML quality test suite |

## US-012: Darija/Arabic Text Normalization

User Story: As a pipeline utility, I want to normalize Darija transcription text so that downstream LLM extraction handles dialectal variations consistently.

Priority: P2 | Points: 3 | Type: AI/ML

Acceptance Criteria:

☐  Common Darija abbreviations expanded

☐  Number words converted to digits (tlata -> 3)

☐  French loan words in Arabic script handled

☐  Normalization applied before LLM extraction

GitHub Issues:

| Issue ID | Title |
| --- | --- |
| AQAR-035 | Build Darija text normalization module |
| AQAR-036 | Create normalization test cases |

# Sprint 4: LLM Data Extraction

Weeks: 7-8

Sprint Goal: Extract structured property data from transcriptions using Claude with versioned prompts.

Capacity: 4 stories, 19 points, 11 issues

| ID | User Story | Priority | Points | Type | Title |
| --- | --- | --- | --- | --- | --- |
| US-013 | As a pipeline stage, I want to extract structured property data from transcriptions using Claude ... | P0 | 8 | AI/ML | Claude Property Extraction |
| US-014 | As a researcher, I want to version-control prompts and track which version extracted each propert... | P1 | 3 | AI/ML | Prompt Version Management |
| US-015 | As an operator, I want low-confidence extractions flagged for manual review so that data quality ... | P1 | 3 | Backend | Extraction Quality Review |
| US-016 | As a researcher, I want to benchmark extraction accuracy against manually annotated properties so... | P1 | 5 | AI/ML | LLM Extraction Benchmarks |

## US-013: Claude Property Extraction

User Story: As a pipeline stage, I want to extract structured property data from transcriptions using Claude so that unstructured speech becomes searchable listings.

Priority: P0 | Points: 8 | Type: AI/ML

Acceptance Criteria:

☐  Transcript text sent to Claude API with property extraction prompt

☐  Response parsed into PropertyCreate schema

☐  Per-field confidence scores captured

☐  Prompt version tagged on each extraction for traceability

☐  Retry with exponential backoff on API failures

GitHub Issues:

| Issue ID | Title |
| --- | --- |
| AQAR-037 | Implement LLM extraction Celery task |
| AQAR-038 | Create property extraction prompt v1.0 |
| AQAR-039 | Build response parser with validation |
| AQAR-040 | Add retry logic with tenacity |

## US-014: Prompt Version Management

User Story: As a researcher, I want to version-control prompts and track which version extracted each property so that I can measure prompt improvement for my thesis.

Priority: P1 | Points: 3 | Type: AI/ML

Acceptance Criteria:

☐  Prompts stored in prompts/ directory with version tags

☐  Property.prompt_version records which prompt extracted the data

☐  A/B testing possible by routing to different prompt versions

☐  Prompt changelog maintained for thesis documentation

GitHub Issues:

| Issue ID | Title |
| --- | --- |
| AQAR-041 | Implement prompt loader with version tagging |
| AQAR-042 | Add prompt_version to extraction pipeline |

## US-015: Extraction Quality Review

User Story: As an operator, I want low-confidence extractions flagged for manual review so that data quality is maintained.

Priority: P1 | Points: 3 | Type: Backend

Acceptance Criteria:

☐  Properties with overall confidence < 0.6 have needs_review=True

☐  GET /api/v1/properties?needs_review=true filters flagged properties

☐  Review dashboard shows extraction vs transcript side-by-side (Phase 7)

GitHub Issues:

| Issue ID | Title |
| --- | --- |
| AQAR-043 | Implement confidence threshold flagging |
| AQAR-044 | Add needs_review filter to properties endpoint |

## US-016: LLM Extraction Benchmarks

User Story: As a researcher, I want to benchmark extraction accuracy against manually annotated properties so that I can quantify LLM performance for my thesis.

Priority: P1 | Points: 5 | Type: AI/ML

Acceptance Criteria:

☐  Golden dataset: 10+ videos with manually extracted property data

☐  Field-level accuracy metrics (price, area, rooms, location)

☐  Overall extraction F1 score calculated

☐  Benchmark results exportable for thesis tables

GitHub Issues:

| Issue ID | Title |
| --- | --- |
| AQAR-045 | Create extraction golden dataset |
| AQAR-046 | Implement field-level accuracy scoring |
| AQAR-047 | Build benchmark reporting utility |

# Sprint 5: Geocoding & Storage

Weeks: 9-10

Sprint Goal: Resolve property locations to coordinates using geocoding and build the search index.

Capacity: 4 stories, 18 points, 12 issues

| ID | User Story | Priority | Points | Type | Title |
| --- | --- | --- | --- | --- | --- |
| US-017 | As a pipeline stage, I want to geocode extracted location text to GPS coordinates so that propert... | P0 | 5 | Pipeline | Location Geocoding |
| US-018 | As a geocoding enhancer, I want a local gazetteer of Tangier neighborhoods and landmarks so that ... | P1 | 5 | Pipeline | Tangier Neighborhood Gazetteer |
| US-019 | As a backend service, I want properties indexed in Meilisearch so that users can perform fast ful... | P0 | 5 | Backend | Meilisearch Index |
| US-020 | As a user, I want to search for properties within a radius of a point on the map so that I can fi... | P1 | 3 | Backend | Spatial Queries |

## US-017: Location Geocoding

User Story: As a pipeline stage, I want to geocode extracted location text to GPS coordinates so that properties can be displayed on a map.

Priority: P0 | Points: 5 | Type: Pipeline

Acceptance Criteria:

☐  Location text (neighborhood, address) sent to geocoding provider

☐  Nominatim used as default (free, no API key required)

☐  Google Maps API available as fallback

☐  Coordinates stored in Location table with PostGIS geometry

☐  Geocoding confidence score recorded

GitHub Issues:

| Issue ID | Title |
| --- | --- |
| AQAR-048 | Implement geocoding Celery task |
| AQAR-049 | Build Nominatim geocoding provider |
| AQAR-050 | Build Google Maps geocoding provider |
| AQAR-051 | Create local gazetteer for Tangier neighborhoods |

## US-018: Tangier Neighborhood Gazetteer

User Story: As a geocoding enhancer, I want a local gazetteer of Tangier neighborhoods and landmarks so that Darija place names resolve to accurate coordinates.

Priority: P1 | Points: 5 | Type: Pipeline

Acceptance Criteria:

☐  JSON gazetteer mapping 50+ Tangier neighborhood names (Arabic + French + Darija) to coordinates

☐  Fuzzy matching handles spelling variations

☐  Gazetteer checked before external geocoding APIs

☐  Coverage includes: Iberia, Marshan, Malabata, Boukhalef, Val Fleuri, Mesnana, etc.

GitHub Issues:

| Issue ID | Title |
| --- | --- |
| AQAR-052 | Research and compile Tangier neighborhood coordinates |
| AQAR-053 | Implement fuzzy gazetteer lookup |
| AQAR-054 | Add gazetteer tests with Darija spelling variants |

## US-019: Meilisearch Index

User Story: As a backend service, I want properties indexed in Meilisearch so that users can perform fast full-text search with Arabic support.

Priority: P0 | Points: 5 | Type: Backend

Acceptance Criteria:

☐  Properties synced to Meilisearch index on creation/update

☐  Searchable fields: title, description, neighborhood, city

☐  Filterable fields: property_type, listing_type, price, area_sqm, rooms

☐  Sortable fields: price, area_sqm, created_at

☐  Arabic tokenization configured

GitHub Issues:

| Issue ID | Title |
| --- | --- |
| AQAR-055 | Create Meilisearch index configuration |
| AQAR-056 | Implement property sync to Meilisearch |
| AQAR-057 | Configure Arabic tokenization settings |

## US-020: Spatial Queries

User Story: As a user, I want to search for properties within a radius of a point on the map so that I can find homes near my workplace or school.

Priority: P1 | Points: 3 | Type: Backend

Acceptance Criteria:

☐  GET /api/v1/properties?lat=35.78&lng=-5.81&radius_km=2 filters by distance

☐  PostGIS ST_DWithin used for efficient spatial filtering

☐  Results include distance from search center

GitHub Issues:

| Issue ID | Title |
| --- | --- |
| AQAR-058 | Implement spatial query in properties endpoint |
| AQAR-059 | Add distance calculation to response |

# Sprint 6: API & Search

Weeks: 11-12

Sprint Goal: Complete REST API with search, filtering, pagination, and statistics.

Capacity: 4 stories, 15 points, 10 issues

| ID | User Story | Priority | Points | Type | Title |
| --- | --- | --- | --- | --- | --- |
| US-021 | As a frontend developer, I want a comprehensive property list API with filtering and pagination s... | P0 | 5 | Backend | Property List & Filter API |
| US-022 | As a property seeker, I want to search for properties using natural language so that I can find l... | P0 | 5 | Backend | Full-Text Search |
| US-023 | As a thesis reviewer, I want system statistics so that I can evaluate the pipeline's performance ... | P1 | 3 | Backend | Statistics Dashboard API |
| US-024 | As a developer, I want interactive API documentation so that frontend and mobile developers can i... | P2 | 2 | Backend | API Documentation |

## US-021: Property List & Filter API

User Story: As a frontend developer, I want a comprehensive property list API with filtering and pagination so that I can build the search interface.

Priority: P0 | Points: 5 | Type: Backend

Acceptance Criteria:

☐  GET /api/v1/properties supports: property_type, listing_type, price range, area range, rooms, neighborhood filters

☐  Pagination with page/per_page (max 100 per page)

☐  Sorting by price, area, created_at (asc/desc)

☐  Response includes total count and has_next flag

GitHub Issues:

| Issue ID | Title |
| --- | --- |
| AQAR-060 | Complete property list endpoint with all filters |
| AQAR-061 | Add pagination and sorting |
| AQAR-062 | Write property API integration tests |

## US-022: Full-Text Search

User Story: As a property seeker, I want to search for properties using natural language so that I can find listings matching my description.

Priority: P0 | Points: 5 | Type: Backend

Acceptance Criteria:

☐  GET /api/v1/search?q=apartment+iberia queries Meilisearch

☐  Results ranked by relevance

☐  Highlights returned for matched terms

☐  Search works in Arabic and French

GitHub Issues:

| Issue ID | Title |
| --- | --- |
| AQAR-063 | Implement search endpoint with Meilisearch |
| AQAR-064 | Configure search ranking rules |
| AQAR-065 | Add search result highlighting |

## US-023: Statistics Dashboard API

User Story: As a thesis reviewer, I want system statistics so that I can evaluate the pipeline's performance and coverage.

Priority: P1 | Points: 3 | Type: Backend

Acceptance Criteria:

☐  GET /api/v1/stats returns: total_videos, total_properties, total_published, processing stats

☐  Average extraction confidence reported

☐  Per-neighborhood property count available

☐  API response time < 500ms

GitHub Issues:

| Issue ID | Title |
| --- | --- |
| AQAR-066 | Implement statistics aggregation queries |
| AQAR-067 | Add per-neighborhood breakdown endpoint |

## US-024: API Documentation

User Story: As a developer, I want interactive API documentation so that frontend and mobile developers can integrate easily.

Priority: P2 | Points: 2 | Type: Backend

Acceptance Criteria:

☐  Swagger UI at /docs with all endpoints documented

☐  ReDoc at /redoc for alternative documentation

☐  All request/response schemas documented with examples

☐  Authentication headers documented (future)

GitHub Issues:

| Issue ID | Title |
| --- | --- |
| AQAR-068 | Add OpenAPI examples to all schemas |
| AQAR-069 | Write API usage guide in docs/ |

# Sprint 7: Web Portal

Weeks: 13-14

Sprint Goal: Next.js web portal with property search, map view, and detail pages.

Capacity: 4 stories, 21 points, 14 issues

| ID | User Story | Priority | Points | Type | Title |
| --- | --- | --- | --- | --- | --- |
| US-025 | As a property seeker, I want a search page with filters and results so that I can browse availabl... | P0 | 8 | Frontend | Property Search Page |
| US-026 | As a property seeker, I want to see properties on an interactive map so that I can understand loc... | P0 | 5 | Frontend | Map View |
| US-027 | As a property seeker, I want a detailed property page with all extracted information and the sour... | P0 | 5 | Frontend | Property Detail Page |
| US-028 | As a Moroccan user, I want the interface available in Arabic and French so that I can use it in m... | P2 | 3 | Frontend | Arabic/French Bilingual UI |

## US-025: Property Search Page

User Story: As a property seeker, I want a search page with filters and results so that I can browse available properties.

Priority: P0 | Points: 8 | Type: Frontend

Acceptance Criteria:

☐  Search bar with autocomplete for neighborhoods

☐  Filter sidebar: property type, listing type, price range, area range, rooms

☐  Results grid with property cards (image, price, area, location)

☐  Pagination or infinite scroll

☐  SSR for SEO (property detail pages)

GitHub Issues:

| Issue ID | Title |
| --- | --- |
| AQAR-070 | Create Next.js app with Tailwind |
| AQAR-071 | Build search bar with Meilisearch client |
| AQAR-072 | Build filter sidebar component |
| AQAR-073 | Build property card grid |

## US-026: Map View

User Story: As a property seeker, I want to see properties on an interactive map so that I can understand locations geographically.

Priority: P0 | Points: 5 | Type: Frontend

Acceptance Criteria:

☐  Mapbox/Leaflet map centered on Tangier

☐  Property markers clustered at zoom levels

☐  Click marker to see property card popup

☐  Map synced with search filters (filter updates map)

☐  Responsive on mobile browsers

GitHub Issues:

| Issue ID | Title |
| --- | --- |
| AQAR-074 | Integrate Mapbox GL JS |
| AQAR-075 | Implement marker clustering |
| AQAR-076 | Build property popup component |
| AQAR-077 | Sync map with search filters |

## US-027: Property Detail Page

User Story: As a property seeker, I want a detailed property page with all extracted information and the source video so that I can evaluate the listing.

Priority: P0 | Points: 5 | Type: Frontend

Acceptance Criteria:

☐  SSR page at /property/[id] for SEO

☐  All extracted fields displayed (price, area, rooms, legal status, etc.)

☐  Embedded YouTube video player (at relevant timestamp if available)

☐  Location shown on mini-map

☐  Confidence indicator showing extraction reliability

GitHub Issues:

| Issue ID | Title |
| --- | --- |
| AQAR-078 | Build property detail page with SSR |
| AQAR-079 | Embed YouTube player component |
| AQAR-080 | Build confidence indicator widget |

## US-028: Arabic/French Bilingual UI

User Story: As a Moroccan user, I want the interface available in Arabic and French so that I can use it in my preferred language.

Priority: P2 | Points: 3 | Type: Frontend

Acceptance Criteria:

☐  next-intl or similar i18n library configured

☐  RTL layout support for Arabic

☐  Language switcher in navbar

☐  Property descriptions in both languages (where generated)

GitHub Issues:

| Issue ID | Title |
| --- | --- |
| AQAR-081 | Configure i18n with next-intl |
| AQAR-082 | Add Arabic translations |
| AQAR-083 | Implement RTL layout support |

# Sprint 8: Mobile App

Weeks: 15-16

Sprint Goal: React Native mobile app with property search, map, and push notifications.

Capacity: 3 stories, 16 points, 10 issues

| ID | User Story | Priority | Points | Type | Title |
| --- | --- | --- | --- | --- | --- |
| US-029 | As a mobile user, I want to search and filter properties on my phone so that I can browse listing... | P0 | 8 | Mobile | Mobile Property Search |
| US-030 | As a mobile user, I want to view properties on a map with my current location so that I can find ... | P1 | 5 | Mobile | Mobile Map View |
| US-031 | As a mobile user, I want to view full property details with the source video so that I can evalua... | P1 | 3 | Mobile | Property Detail Screen |

## US-029: Mobile Property Search

User Story: As a mobile user, I want to search and filter properties on my phone so that I can browse listings on the go.

Priority: P0 | Points: 8 | Type: Mobile

Acceptance Criteria:

☐  Expo/React Native app with search screen

☐  Filter bottom sheet with property type, price range, area

☐  Property list with card layout

☐  Pull-to-refresh and infinite scroll

☐  Works on iOS and Android

GitHub Issues:

| Issue ID | Title |
| --- | --- |
| AQAR-084 | Initialize Expo project with navigation |
| AQAR-085 | Build search screen with filters |
| AQAR-086 | Build property card list component |
| AQAR-087 | Connect to FastAPI backend |

## US-030: Mobile Map View

User Story: As a mobile user, I want to view properties on a map with my current location so that I can find nearby listings.

Priority: P1 | Points: 5 | Type: Mobile

Acceptance Criteria:

☐  react-native-maps with property markers

☐  Current location shown with radius indicator

☐  Tap marker opens property preview card

☐  Map clustered at lower zoom levels

GitHub Issues:

| Issue ID | Title |
| --- | --- |
| AQAR-088 | Integrate react-native-maps |
| AQAR-089 | Implement location-based search |
| AQAR-090 | Build marker preview card |

## US-031: Property Detail Screen

User Story: As a mobile user, I want to view full property details with the source video so that I can evaluate listings.

Priority: P1 | Points: 3 | Type: Mobile

Acceptance Criteria:

☐  Full property detail screen with all fields

☐  In-app YouTube video player

☐  Share property via native share sheet

☐  Deep link support: aqar.ai/property/[id]

GitHub Issues:

| Issue ID | Title |
| --- | --- |
| AQAR-091 | Build property detail screen |
| AQAR-092 | Integrate video player |
| AQAR-093 | Add share and deep linking |

# Sprint 9: Quality & Monitoring

Weeks: 17-18

Sprint Goal: Production observability, error tracking, and pipeline quality metrics for thesis evaluation.

Capacity: 3 stories, 13 points, 8 issues

| ID | User Story | Priority | Points | Type | Title |
| --- | --- | --- | --- | --- | --- |
| US-032 | As an operator, I want centralized error tracking and structured logging so that I can diagnose i... | P0 | 3 | DevOps | Error Tracking & Logging |
| US-033 | As a thesis author, I want a metrics dashboard showing pipeline performance so that I can include... | P1 | 5 | DevOps | Pipeline Metrics Dashboard |
| US-034 | As a developer, I want an end-to-end test that processes a real video through the entire pipeline... | P1 | 5 | Testing | End-to-End Pipeline Test |

## US-032: Error Tracking & Logging

User Story: As an operator, I want centralized error tracking and structured logging so that I can diagnose issues quickly.

Priority: P0 | Points: 3 | Type: DevOps

Acceptance Criteria:

☐  Sentry integration for API and pipeline workers

☐  Structured logging with structlog (JSON format)

☐  Request ID propagated through pipeline stages

☐  Error alerts configured for critical failures

GitHub Issues:

| Issue ID | Title |
| --- | --- |
| AQAR-094 | Integrate Sentry SDK |
| AQAR-095 | Configure structlog for all services |
| AQAR-096 | Add request ID propagation |

## US-033: Pipeline Metrics Dashboard

User Story: As a thesis author, I want a metrics dashboard showing pipeline performance so that I can include quantitative results in my thesis.

Priority: P1 | Points: 5 | Type: DevOps

Acceptance Criteria:

☐  Grafana dashboard with: videos processed/day, avg processing time per stage

☐  Transcription WER trends over time

☐  Extraction confidence distribution chart

☐  Geocoding success rate by neighborhood

☐  Dashboard exportable as images for thesis

GitHub Issues:

| Issue ID | Title |
| --- | --- |
| AQAR-097 | Set up Grafana Cloud with Prometheus metrics |
| AQAR-098 | Export pipeline stage metrics |
| AQAR-099 | Build thesis metrics dashboard |

## US-034: End-to-End Pipeline Test

User Story: As a developer, I want an end-to-end test that processes a real video through the entire pipeline so that I can validate the complete flow.

Priority: P1 | Points: 5 | Type: Testing

Acceptance Criteria:

☐  Test processes a known YouTube video URL

☐  Validates: ingestion, transcription, extraction, geocoding all succeed

☐  Verifies property is created with non-null fields

☐  Verifies location has valid coordinates

☐  Test runs in CI with mocked external APIs

GitHub Issues:

| Issue ID | Title |
| --- | --- |
| AQAR-100 | Write end-to-end pipeline integration test |
| AQAR-101 | Create external API mocks for CI |

# Sprint 10: Deployment & Thesis

Weeks: 19-20

Sprint Goal: Production deployment, thesis documentation, and final presentation.

Capacity: 3 stories, 16 points, 11 issues

| ID | User Story | Priority | Points | Type | Title |
| --- | --- | --- | --- | --- | --- |
| US-035 | As a thesis presenter, I want the system deployed publicly so that reviewers can interact with th... | P0 | 5 | DevOps | Production Deployment |
| US-036 | As a thesis author, I want comprehensive documentation of the system architecture, methodology, a... | P0 | 8 | Documentation | Thesis Documentation |
| US-037 | As a thesis presenter, I want the system populated with real processed data so that I can give a ... | P1 | 3 | Data | Demo & Seed Data |

## US-035: Production Deployment

User Story: As a thesis presenter, I want the system deployed publicly so that reviewers can interact with the live application.

Priority: P0 | Points: 5 | Type: DevOps

Acceptance Criteria:

☐  API deployed to Railway or Fly.io

☐  Web portal deployed to Vercel

☐  Database hosted on Railway PostgreSQL (with PostGIS)

☐  HTTPS enabled with custom domain (aqar.ai or subdomain)

☐  Environment variables securely managed

GitHub Issues:

| Issue ID | Title |
| --- | --- |
| AQAR-102 | Deploy API to Railway/Fly.io |
| AQAR-103 | Deploy web to Vercel |
| AQAR-104 | Configure production database |
| AQAR-105 | Set up domain and SSL |

## US-036: Thesis Documentation

User Story: As a thesis author, I want comprehensive documentation of the system architecture, methodology, and results so that I can write my thesis efficiently.

Priority: P0 | Points: 8 | Type: Documentation

Acceptance Criteria:

☐  Architecture diagrams (C4 model: context, container, component)

☐  Methodology chapter: pipeline design, prompt engineering approach, evaluation metrics

☐  Results chapter: WER benchmarks, extraction accuracy, geocoding coverage

☐  Comparison with existing solutions (Avito, Mubawab manual listings)

☐  All figures and tables generated from actual system metrics

GitHub Issues:

| Issue ID | Title |
| --- | --- |
| AQAR-106 | Generate C4 architecture diagrams |
| AQAR-107 | Export pipeline performance metrics |
| AQAR-108 | Write evaluation methodology section |
| AQAR-109 | Compile comparison analysis |

## US-037: Demo & Seed Data

User Story: As a thesis presenter, I want the system populated with real processed data so that I can give a compelling live demo.

Priority: P1 | Points: 3 | Type: Data

Acceptance Criteria:

☐  50+ real properties processed through the pipeline

☐  Coverage across 10+ Tangier neighborhoods

☐  Mix of apartments, houses, villas, land

☐  make seed populates demo data for fresh deployments

GitHub Issues:

| Issue ID | Title |
| --- | --- |
| AQAR-110 | Process 50+ real YouTube videos |
| AQAR-111 | Create demo seed script |
| AQAR-112 | Verify data quality and coverage |

# Complete Issue Index

All 112 GitHub issues organized by sprint and priority for backlog management.

| Issue | Sprint | Title | Priority | Story |
| --- | --- | --- | --- | --- |
| AQAR-001 | S1 | Create monorepo directory structure | P0 | Project Scaffold & Monorepo |
| AQAR-002 | S1 | Configure root pyproject.toml with ruff/mypy/pytest | P0 | Project Scaffold & Monorepo |
| AQAR-003 | S1 | Write Makefile developer commands | P0 | Project Scaffold & Monorepo |
| AQAR-004 | S1 | Write Dockerfile.api (multi-stage) | P0 | Docker Development Stack |
| AQAR-005 | S1 | Write Dockerfile.worker (with FFmpeg) | P0 | Docker Development Stack |
| AQAR-006 | S1 | Configure docker-compose.yml with all services | P0 | Docker Development Stack |
| AQAR-007 | S1 | Create init-db.sql with PostGIS extensions | P0 | Docker Development Stack |
| AQAR-008 | S1 | Define SQLAlchemy models in packages/db | P0 | Database Schema & Migrations |
| AQAR-009 | S1 | Configure Alembic for async migrations | P0 | Database Schema & Migrations |
| AQAR-010 | S1 | Generate and run initial migration | P0 | Database Schema & Migrations |
| AQAR-011 | S1 | Add PostGIS spatial indexes | P0 | Database Schema & Migrations |
| AQAR-012 | S1 | Create .github/workflows/ci.yml | P0 | CI/CD Pipeline |
| AQAR-013 | S1 | Configure pre-commit hooks | P0 | CI/CD Pipeline |
| AQAR-014 | S1 | Write initial unit test stubs | P0 | CI/CD Pipeline |
| AQAR-015 | S1 | Implement /health and /health/ready endpoints | P1 | Health Check API |
| AQAR-016 | S1 | Add health check integration tests | P1 | Health Check API |
| AQAR-017 | S2 | Implement discover_videos Celery task | P0 | YouTube Channel Discovery |
| AQAR-018 | S2 | Create YouTube channel configuration (YAML) | P0 | YouTube Channel Discovery |
| AQAR-019 | S2 | Write yt-dlp metadata extraction wrapper | P0 | YouTube Channel Discovery |
| AQAR-020 | S2 | Implement audio extraction with yt-dlp | P0 | Audio Extraction |
| AQAR-021 | S2 | Add FFmpeg audio conversion (WAV 16kHz) | P0 | Audio Extraction |
| AQAR-022 | S2 | Implement download cleanup after transcription | P0 | Audio Extraction |
| AQAR-023 | S2 | Implement ProcessingJob state machine | P0 | Processing Job Tracking |
| AQAR-024 | S2 | Add stage timing instrumentation | P0 | Processing Job Tracking |
| AQAR-025 | S2 | Implement retry-failed-jobs Celery task | P0 | Processing Job Tracking |
| AQAR-026 | S2 | Implement pipeline submit endpoint | P1 | Pipeline Submit API |
| AQAR-027 | S2 | Add YouTube URL validation | P1 | Pipeline Submit API |
| AQAR-028 | S2 | Connect endpoint to Celery task dispatch | P1 | Pipeline Submit API |
| AQAR-029 | S3 | Implement Whisper transcription Celery task | P0 | Whisper Transcription |
| AQAR-030 | S3 | Configure Whisper model loading (CPU/CUDA) | P0 | Whisper Transcription |
| AQAR-031 | S3 | Implement segment extraction and storage | P0 | Whisper Transcription |
| AQAR-032 | S3 | Collect and annotate golden dataset (10 clips) | P1 | Transcription Quality Baseline |
| AQAR-033 | S3 | Implement WER calculation utility | P1 | Transcription Quality Baseline |
| AQAR-034 | S3 | Create ML quality test suite | P1 | Transcription Quality Baseline |
| AQAR-035 | S3 | Build Darija text normalization module | P2 | Darija/Arabic Text Normalization |
| AQAR-036 | S3 | Create normalization test cases | P2 | Darija/Arabic Text Normalization |
| AQAR-037 | S4 | Implement LLM extraction Celery task | P0 | Claude Property Extraction |
| AQAR-038 | S4 | Create property extraction prompt v1.0 | P0 | Claude Property Extraction |
| AQAR-039 | S4 | Build response parser with validation | P0 | Claude Property Extraction |
| AQAR-040 | S4 | Add retry logic with tenacity | P0 | Claude Property Extraction |
| AQAR-041 | S4 | Implement prompt loader with version tagging | P1 | Prompt Version Management |
| AQAR-042 | S4 | Add prompt_version to extraction pipeline | P1 | Prompt Version Management |
| AQAR-043 | S4 | Implement confidence threshold flagging | P1 | Extraction Quality Review |
| AQAR-044 | S4 | Add needs_review filter to properties endpoint | P1 | Extraction Quality Review |
| AQAR-045 | S4 | Create extraction golden dataset | P1 | LLM Extraction Benchmarks |
| AQAR-046 | S4 | Implement field-level accuracy scoring | P1 | LLM Extraction Benchmarks |
| AQAR-047 | S4 | Build benchmark reporting utility | P1 | LLM Extraction Benchmarks |
| AQAR-048 | S5 | Implement geocoding Celery task | P0 | Location Geocoding |
| AQAR-049 | S5 | Build Nominatim geocoding provider | P0 | Location Geocoding |
| AQAR-050 | S5 | Build Google Maps geocoding provider | P0 | Location Geocoding |
| AQAR-051 | S5 | Create local gazetteer for Tangier neighborhoods | P0 | Location Geocoding |
| AQAR-052 | S5 | Research and compile Tangier neighborhood coordinates | P1 | Tangier Neighborhood Gazetteer |
| AQAR-053 | S5 | Implement fuzzy gazetteer lookup | P1 | Tangier Neighborhood Gazetteer |
| AQAR-054 | S5 | Add gazetteer tests with Darija spelling variants | P1 | Tangier Neighborhood Gazetteer |
| AQAR-055 | S5 | Create Meilisearch index configuration | P0 | Meilisearch Index |
| AQAR-056 | S5 | Implement property sync to Meilisearch | P0 | Meilisearch Index |
| AQAR-057 | S5 | Configure Arabic tokenization settings | P0 | Meilisearch Index |
| AQAR-058 | S5 | Implement spatial query in properties endpoint | P1 | Spatial Queries |
| AQAR-059 | S5 | Add distance calculation to response | P1 | Spatial Queries |
| AQAR-060 | S6 | Complete property list endpoint with all filters | P0 | Property List & Filter API |
| AQAR-061 | S6 | Add pagination and sorting | P0 | Property List & Filter API |
| AQAR-062 | S6 | Write property API integration tests | P0 | Property List & Filter API |
| AQAR-063 | S6 | Implement search endpoint with Meilisearch | P0 | Full-Text Search |
| AQAR-064 | S6 | Configure search ranking rules | P0 | Full-Text Search |
| AQAR-065 | S6 | Add search result highlighting | P0 | Full-Text Search |
| AQAR-066 | S6 | Implement statistics aggregation queries | P1 | Statistics Dashboard API |
| AQAR-067 | S6 | Add per-neighborhood breakdown endpoint | P1 | Statistics Dashboard API |
| AQAR-068 | S6 | Add OpenAPI examples to all schemas | P2 | API Documentation |
| AQAR-069 | S6 | Write API usage guide in docs/ | P2 | API Documentation |
| AQAR-070 | S7 | Create Next.js app with Tailwind | P0 | Property Search Page |
| AQAR-071 | S7 | Build search bar with Meilisearch client | P0 | Property Search Page |
| AQAR-072 | S7 | Build filter sidebar component | P0 | Property Search Page |
| AQAR-073 | S7 | Build property card grid | P0 | Property Search Page |
| AQAR-074 | S7 | Integrate Mapbox GL JS | P0 | Map View |
| AQAR-075 | S7 | Implement marker clustering | P0 | Map View |
| AQAR-076 | S7 | Build property popup component | P0 | Map View |
| AQAR-077 | S7 | Sync map with search filters | P0 | Map View |
| AQAR-078 | S7 | Build property detail page with SSR | P0 | Property Detail Page |
| AQAR-079 | S7 | Embed YouTube player component | P0 | Property Detail Page |
| AQAR-080 | S7 | Build confidence indicator widget | P0 | Property Detail Page |
| AQAR-081 | S7 | Configure i18n with next-intl | P2 | Arabic/French Bilingual UI |
| AQAR-082 | S7 | Add Arabic translations | P2 | Arabic/French Bilingual UI |
| AQAR-083 | S7 | Implement RTL layout support | P2 | Arabic/French Bilingual UI |
| AQAR-084 | S8 | Initialize Expo project with navigation | P0 | Mobile Property Search |
| AQAR-085 | S8 | Build search screen with filters | P0 | Mobile Property Search |
| AQAR-086 | S8 | Build property card list component | P0 | Mobile Property Search |
| AQAR-087 | S8 | Connect to FastAPI backend | P0 | Mobile Property Search |
| AQAR-088 | S8 | Integrate react-native-maps | P1 | Mobile Map View |
| AQAR-089 | S8 | Implement location-based search | P1 | Mobile Map View |
| AQAR-090 | S8 | Build marker preview card | P1 | Mobile Map View |
| AQAR-091 | S8 | Build property detail screen | P1 | Property Detail Screen |
| AQAR-092 | S8 | Integrate video player | P1 | Property Detail Screen |
| AQAR-093 | S8 | Add share and deep linking | P1 | Property Detail Screen |
| AQAR-094 | S9 | Integrate Sentry SDK | P0 | Error Tracking & Logging |
| AQAR-095 | S9 | Configure structlog for all services | P0 | Error Tracking & Logging |
| AQAR-096 | S9 | Add request ID propagation | P0 | Error Tracking & Logging |
| AQAR-097 | S9 | Set up Grafana Cloud with Prometheus metrics | P1 | Pipeline Metrics Dashboard |
| AQAR-098 | S9 | Export pipeline stage metrics | P1 | Pipeline Metrics Dashboard |
| AQAR-099 | S9 | Build thesis metrics dashboard | P1 | Pipeline Metrics Dashboard |
| AQAR-100 | S9 | Write end-to-end pipeline integration test | P1 | End-to-End Pipeline Test |
| AQAR-101 | S9 | Create external API mocks for CI | P1 | End-to-End Pipeline Test |
| AQAR-102 | S10 | Deploy API to Railway/Fly.io | P0 | Production Deployment |
| AQAR-103 | S10 | Deploy web to Vercel | P0 | Production Deployment |
| AQAR-104 | S10 | Configure production database | P0 | Production Deployment |
| AQAR-105 | S10 | Set up domain and SSL | P0 | Production Deployment |
| AQAR-106 | S10 | Generate C4 architecture diagrams | P0 | Thesis Documentation |
| AQAR-107 | S10 | Export pipeline performance metrics | P0 | Thesis Documentation |
| AQAR-108 | S10 | Write evaluation methodology section | P0 | Thesis Documentation |
| AQAR-109 | S10 | Compile comparison analysis | P0 | Thesis Documentation |
| AQAR-110 | S10 | Process 50+ real YouTube videos | P1 | Demo & Seed Data |
| AQAR-111 | S10 | Create demo seed script | P1 | Demo & Seed Data |
| AQAR-112 | S10 | Verify data quality and coverage | P1 | Demo & Seed Data |